Preparation of a Software Project Plan Covering Scope, Timeline, and Team Roles

Aim

To prepare a detailed software project plan covering project scope, schedule/timeline, resource allocation, and team roles for the development of a real-world sample application (E-Commerce Web & Mobile Application).

Objective

Define the in-scope and out-of-scope functional requirements for the target application.

Establish a phased timeline and sprint breakdown for the software development life cycle.

Define team roles, responsibilities, and key project stakeholders.

Identify resource requirements, risk factors, and delivery milestones.

Selected Software Application

E-Commerce Web and Mobile Application (e.g., Online Retail Store)

Overview

The sample application is an end-to-end e-commerce platform that enables customers to browse products, manage shopping carts, process payments online, and track orders, while providing store administrators with inventory and sales management tools.

Project Scope Definition

In-Scope Features

User Management: Customer registration, login, profile management, password recovery.

Product Catalog: Categorized product browsing, search with filters, product detail pages.

Shopping Cart & Checkout: Cart addition/modification, payment gateway integration (Credit Card, UPI, Net Banking).

Order Management & Tracking: Order confirmation, real-time delivery status, order history.

Admin Portal: Inventory update, order fulfillment control, sales reports, user role management.

Out-of-Scope Features

Multi-vendor marketplace capability (Phase 1 focuses solely on a single-seller store).

AI-driven automated chatbot customer support (deferred to Phase 2).

International currency conversions and cross-border shipping logistics.

Team Roles and Responsibilities

| Role | Key Responsibilities |
| --- | --- |
| Project Manager (PM) | Overall project oversight, resource allocation, schedule tracking, risk management, and client communication. |
| Product Owner / Business Analyst | Requirement gathering, SRS preparation, defining user stories, managing project backlog. |
| UI/UX Designer | User interface wireframing, high-fidelity mockups, customer experience design, prototype creation. |
| Tech Lead / System Architect | System architecture design, technology stack selection, code reviews, database schema design. |
| Frontend Developers (2) | Developing web and mobile UI components using React and React Native. |
| Backend Developers (2) | Creating RESTful APIs, database management, integration with payment gateways and external services. |
| QA / Test Engineers (2) | Executing unit, integration, performance, and user acceptance testing (UAT). |
| DevOps Engineer | CI/CD pipeline setup, cloud environment setup (AWS/Azure), automated deployment, platform monitoring. |

Project Timeline and Schedule

The total project duration is estimated at 16 Weeks (4 Months), executed across 8 bi-weekly sprints using an Agile development approach.

| Phase | Duration | Activities Covered | Key Deliverables |
| --- | --- | --- | --- |
| Phase 1: Initiation & Planning | Weeks 1 - 2 | Requirement gathering, SRS creation, project plan finalized, team onboarding. | SRS Document, Project Charter |
| Phase 2: System Design | Weeks 3 - 4 | UI/UX wireframes, database schema design, system architecture design. | Design Specs, Wireframes, ERD |
| Phase 3: Sprint 1 & 2 (Core Backend) | Weeks 5 - 8 | Database setup, User Management API, Product Catalog API development. | Working Authentication & Catalog APIs |
| Phase 4: Sprint 3 & 4 (Frontend & Cart) | Weeks 9 - 12 | UI integration, Shopping Cart, Payment Gateway integration, Admin Panel. | Functional Web & Mobile UI |
| Phase 5: Testing & QA | Weeks 13 - 14 | Integration testing, security testing, bug fixing, User Acceptance Testing (UAT). | Test Execution Reports, QA Approval |
| Phase 6: Deployment & Launch | Weeks 15 - 16 | Production environment setup, CI/CD deployment, app store release, project handover. | Live Platform, Final Documentation |

Risk Management Plan

| Risk Event | Severity | Mitigation Strategy |
| --- | --- | --- |
| Scope Creep | High | Implement strict change control procedures and prioritize backlog items during sprint planning. |
| Payment Gateway Delay | Medium | Start third-party API integration early and use sandbox test credentials during development. |
| Resource Availability / Turnover | Medium | Maintain proper documentation and cross-train team members on key project modules. |
| Performance Issues under High Load | High | Perform stress testing early and implement database indexing and server caching. |

Results

A structured software project plan was developed for an E-Commerce Application.

Project scope was clearly demarcated into in-scope functional requirements and out-of-scope boundaries to prevent scope creep.

Team roles and responsibilities were mapped out across 10 project team members.

A 16-week Agile timeline with clear sprint milestones and risk management strategies was established.

Conclusion

Preparing a comprehensive software project plan is crucial for ensuring the predictable and successful delivery of software applications. Clear scope definition prevents project delays, a structured timeline provides clear accountability, and well-defined team roles ensure efficient task execution. Following this project plan ensures optimal resource utilization, timely risk mitigation, and successful application launch.